## Plan
Tasks | Member | Completion Date | Time in hours | Team Lead | Status
Day 1 - 21-06-2018
Understand The SRS | All | 2018-06-21 | 2 | Anannya | Done
Understand the Website Functionality | All | 2018-06-21 | 3 |  | Done
Task Division | All | 2018-06-21 | 1.5 |  | Done
Test Case Scenario Description | All |  | 2
Tasks | Member |  | Time in hours |  | Status
Day 2 - 22-06-2018
Signup Functions for Individual Member | Nidhi |  | Full | Naman
Login Functions for Individual Member | Siddharth |  | Full
Signup Functions for Non-Individual Members | Naman |  | Full
Login Functions for Non-Individual Members | Naman |  | Full
Transaction - trading, Transaction Entry, View Transaction | Avi, Vibhas |  | Full | Nidhi
Term Deposit - Fixed Deposit | Anannya,Rishabh |  | Full
Reporting | Siddharth , Nidhi |  | Full
Tasks | Member |  | Time in hours |  | Status
Day 3 - 23-06-2108
Continued From Day 2 |  |  | Full | Siddharth
Tasks | Member |  | Time in hours |  | Status
Day 4 - 25-06-2018
Component Checks to be Performed |  |  | 3 | Rishabh
Project Integration |  |  | 3
Simulation |  |  | 3
Tasks | Member |  | Time in hours |  | Status
Day 5 - 27-06-2018
Presentation | Anannya, Naman |  | 2 | Avi
Excel Sheet Integration | Siddharth , Vibhas |  | 3
file Integration, Simulation | Rishabh , Nidhi |  | 2
Readme Doc | Avi |  | 2 | Vibhas
Presentation Demo Practice | All |  | 2

## Test Scenario Description
System Testing Scenarios
ID | Scenario Name | Pre-Conditions | Scenario Description | Post-Conditions | Assumptions
1 | Login | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Login to Individual account with correct credentials | Login Successful | All correct Credentials
2 | Login | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Login to Individual Account if the credentials are incorrect | Login Unsuccessful | Username or Password is incorrect
3 | Login | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Login to Non-Individual account with correct credentials | Login Successful | All correct Credentials
4 | Login | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Login to on-Individual Account if the credentials are incorrect | Login Unsuccessful | Username or Password is incorrect
5 | Logout | 1. Internet is accessible 2.site is up and running. 3.supplier has an account. | Successful Logout | Logout is Successful | Selected logout option
6 | Logout | 1. Internet is accessible 2.site is up and running. 3.supplier has an account. | Logout is Successful | Logout is Successful | Selected Text Logout option in footer.
7 | Logout | 1. Internet is accessible 2.site is up and running. 3.supplier has an account. | Logout is not Successful | Logout is not Successful | Member not logged in.
8 | Registration | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Registration to Individual account | Registration is successful | All credentials entered correctly.
9 | Registration | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Register to Individual account | Registration is notsuccessful | Credentials not entered correctly or values left blank.
10 | Registration | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Registration to Non-Individual account | Registration is successful | All credentials entered correctly.
11 | Registration | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Register to Non-Individual account | Registration is notsuccessful | Credentials not entered correctly or values left blank.
12 | RegistrationConfirm | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Registration to Individual account | Confirmation is successful | Confirmation action selected correctly.
13 | RegistrationConfirm | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Register to Individual account | Confirmation is not successful | Confirmation action not selected correctly.
14 | RegistrationConfirm | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Registration to Non-Individual account | Confirmation is successful | Confirmation action selected correctly.
15 | RegistrationConfirm | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Register to Non-Individual account | Confirmation is not successful | Confirmation action not selected correctly.
16 | TransactionEntry | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Successfully Register a Transaction by the member. | Transaction is Emntered in the database | All credentials entered correctly.
17 | TransactionEntry | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Successfully Register a Transaction by the member. | Transaction is Emntered in the database | Credentials entered correctly.
18 | FixedDeposit | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Successfully Create a Fixed deposit fund by the member. | Fixed Deposit of particular value is Emntered in the database | All credentials entered correctly.
19 | FixedDeposit | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Successfully Create a Fixed deposit fund by the member. | Fixed Deposit of particular value is Emntered in the database | Credentials entered correctly.
Note on D3: Pre-Condition for the scenario
Note on F3: Post-Condition of the scenario

## TestCaseImplementationValue
Test Case No. | Scenario Id | Pre - Condition | Test Case Description | Test Step No. | Test Step Description | Input Values | Expected Result | Actual Result
1 | TS_Login_001 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Login to Individual account | 1 | Go to SoftPac website | http://205.147.102.59:8080/SoftPac/login
|  |  |  | 2 | Enter the username | beta8
|  |  |  | 3 | Enter the password | beta@123
|  |  |  | 4 | click on Login Button |  | Logged In
2 | TS_Login_002 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Login to Individual Account | 1 | Go to SoftPac website | http://205.147.102.59:8080/SoftPac/login
|  |  |  | 2 | Enter the username | beta8
|  |  |  | 3 | Enter the incorrect password | 123456Google@@@
|  |  |  | 4 | click on Login Button |  | Login Unsuccessful
3 | TS_Login_003 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Login to Individual Account | 1 | Go to SoftPac website | http://205.147.102.59:8080/SoftPac/login
|  |  |  | 2 | Enter the incorrect username | beta444
|  |  |  | 3 | Enter the password | beta@123
|  |  |  | 4 | click on Login Button |  | Login Unsuccessful
4 | TS_Login_004 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Login to Individual Account | 1 | Go to SoftPac website | http://205.147.102.59:8080/SoftPac/login
|  |  |  | 2 | Enter the incorrect username | betaa8
|  |  |  | 3 | Enter the incorrect password | 123456Google@@@
|  |  |  | 4 | click on Login Button |  | Login Unsuccessful
5 | TS_Login_005 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Not Able to Login to Individual Account | 1 | Go to SoftPac website | http://205.147.102.59:8080/SoftPac/login
|  |  |  | 2 | Enter the username | beta8
|  |  |  | 3 | Forgot password
|  |  |  | 4 | click on Login Button |  | Login Unsuccessful
6 | TS_Registration_001 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Registration to Individual account | 1 | Go to SoftPac website | http://205.147.102.59:8080/SoftPac/login
|  |  |  | 2 | Click on Membership
|  |  |  | 3 | Click on Member Registration
|  |  |  | 4 | Click on Individual
|  |  |  | 5 | Select Type | Member
|  |  |  | 6 | Select Account Type | Single
|  |  |  | 7 | Enter Firstname | Anannya
|  |  |  | 8 | Enter Middle Name | Roy
|  |  |  | 9 | Enter Last Name | Chowdhury
|  |  |  | 10 | Enter Gender | Male or Female
|  |  |  | 11 | Enter Date of Birth | 1995-06-28
|  |  |  | 12 | Select Religion | Multi Select
|  |  |  | 13 | Select Occcupation | Farmer
|  |  |  | 14 | Select Land Value | 10000
|  |  |  | 15 | Select Caste | Multi Select
|  |  |  | 16 | Select Class | Multi Select
|  |  |  | 17 | Select Nationality | Indian
|  |  |  | 18 | Father/Husband Name | P.R.Chowdhury
|  |  |  | 19 | Mother Name | A.R.Chowdhury
|  |  |  | 20 | Go to Verification Tab
|  |  |  | 21 | Enter Pan | 111111
|  |  |  | 22 | Enter Voter | 222222
|  |  |  | 23 | Enter Dl | 333333
|  |  |  | 24 | Enter Aadhaar | 444444
|  |  |  | 25 | Enter Passport | 555555
|  |  |  | 26 | Select Form 60 Status | No
|  |  |  | 27 | Select Form 61 | No
|  |  |  | 28 | Go to Address Tab
|  |  |  | 29 | Enter Address | LTI
|  |  |  | 30 | Enter Village Name | Multi Select
|  |  |  | 31 | Enter State | Maharashtra
|  |  |  | 32 | Enter Pincode | 400705
|  |  |  | 33 | Enter Landline Number | 12345678901
|  |  |  | 34 | Enter Mobile Number | 1234567890
|  |  |  | 35 | Enter Mail id | abc@gmail.com
|  |  |  | 36 | Go to Other Tab
|  |  |  | 37 | Enter income | 10000000
|  |  |  | 38 | Enter Education | Multi Select
|  |  |  | 39 | Enter Marital Status | Unmarried
|  |  |  | 40 | Enter Nature Of Activity | Multi Select
|  |  |  | 41 | Click Submit |  | Member Details Saved Sucessfully. Please Upload Photograph.
|  |  |  | 42 | Select Member Id from Member Id List | 118573
|  |  |  | 43 | Choose Image file to upload from System | <Path of image> or <fully qualified name of the image>
|  |  |  | 44 | Click Upload |  | Image Uploaded successfully
|  |  |  | 45 | Select Member Id from Member Id List | 118573
|  |  |  | 46 | Choose Signature Image file to upload from System | <Path of image> or <fully qualified name of the image>
|  |  |  | 47 | Click Upload |  | Image Uploaded successfully
|  |  |  | 48 | Go to membership tab
|  |  |  | 49 | Go to Membership Modification
|  |  |  | 50 | Click on Individual
|  |  |  | 51 | Select Member Id from Member Id List that is yet not confirmed
|  |  |  | 52 | Click actions and then click on confirm
|  |  |  | 53 | Change Value of Land Area as required | 10000
|  |  |  | 54 | Click on Submit |  | Account Successfully Confirmed
7 | TS_Registration_008 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Registration to Individual account | 1 | Go to SoftPac website | http://205.147.102.59:8080/SoftPac/login
|  |  |  | 2 | Click on Membership
|  |  |  | 3 | Click on Member Registration
|  |  |  | 4 | Click on Individual
|  |  |  | 5 | Select Type | Customer
|  |  |  | 6 | Select Account Type | Single
|  |  |  | 7 | Enter Firstname | Anannya
|  |  |  | 8 | Enter Middle Name | Roy
|  |  |  | 9 | Enter Last Name | Chowdhury
|  |  |  | 10 | Enter Gender | Female
|  |  |  | 11 | Enter Date of Birth | 1995-06-28
|  |  |  | 12 | Select Religion | Multi Select
|  |  |  | 13 | Select Occcupation | Farmer
|  |  |  | 14 | Select Land Value | 10000
|  |  |  | 15 | Select Caste | Multi Select
|  |  |  | 16 | Select Class | N/A
|  |  |  | 17 | Select Nationality | Indian
|  |  |  | 18 | Father/Husband Name | P.R.Chowdhury
|  |  |  | 19 | Mother Name | A.R.Chowdhury
|  |  |  | 20 | Go to Verification Tab
|  |  |  | 21 | Enter Pan | 111111
|  |  |  | 22 | Enter Voter | 222222
|  |  |  | 23 | Enter Dl | 333333
|  |  |  | 24 | Enter Aadhaar | 444444
|  |  |  | 25 | Enter Passport | 555555
|  |  |  | 26 | Select Form 60 Status | No
|  |  |  | 27 | Select Form 61 | No
|  |  |  | 28 | Go to Address Tab
|  |  |  | 29 | Enter Address | LTI
|  |  |  | 30 | Enter Village Name | Multi Select
|  |  |  | 31 | Enter State | Maharashtra
|  |  |  | 32 | Enter Pincode | 400705
|  |  |  | 33 | Enter Landline Number | 12345678901
|  |  |  | 34 | Enter Mobile Number | 1234567890
|  |  |  | 35 | Enter Mail id | abc@gmail.com
|  |  |  | 36 | Go to Other Tab
|  |  |  | 37 | Enter income | 10000000
|  |  |  | 38 | Enter Education | Multi Select
|  |  |  | 39 | Enter Marital Status | Unmarried
|  |  |  | 40 | Enter Nature Of Activity | Multi Select
|  |  |  | 41 | Click Submit |  | Member Details Saved Sucessfully. Please Upload Photograph.
|  |  |  | 42 | Select Member Id from Member Id List | 118573
|  |  |  | 43 | Choose Image file to upload from System | <Path of image> or <fully qualified name of the image>
|  |  |  | 44 | Click Upload |  | Image Uploaded successfully
|  |  |  | 45 | Select Member Id from Member Id List | 118573
|  |  |  | 46 | Choose Signature Image file to upload from System | <Path of image> or <fully qualified name of the image>
|  |  |  | 47 | Click Upload |  | Image Uploaded successfully
|  |  |  | 48 | Go to membership tab
|  |  |  | 49 | Go to Membership Modification
|  |  |  | 50 | Click on Individual
|  |  |  | 51 | Select Member Id from Member Id List that is yet not confirmed
|  |  |  | 52 | Click actions and then click on confirm
|  |  |  | 53 | Change Value of Land Area as required | 10000
|  |  |  | 54 | Click on Submit |  | Account Successfully Confirmed
8 | TS_Registration_009 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Registration to Non-Individual account | 1 | Go to SoftPac website | http://205.147.102.59:8080/SoftPac/login
|  |  |  | 2 | Click on Membership
|  |  |  | 3 | Click on Member Registration
|  |  |  | 4 | Click on Non-Individual
|  |  |  | 5 | Select Type | Customer
|  |  |  | 6 | Select Account Type | Single
|  |  |  | 7 | Enter name | Vibhas Sharma
|  |  |  | 8 | Enter operator 1 Name | Rishabh Raghav
|  |  |  | 9 | Enter operator 2 Name | Siddharth Kumar
|  |  |  | 10 | Enter Gender | Male
|  |  |  | 11 | Enter Date of Birth | 1995-06-28
|  |  |  | 12 | Select Religion | Multi Select
|  |  |  | 13 | Select Occcupation | Farmer
|  |  |  | 14 | Select Land Value | 10000
|  |  |  | 15 | Select Caste | Multi Select
|  |  |  | 16 | Select Class | N/A
|  |  |  | 17 | Select Nationality | Indian
|  |  |  | 18 | Father/Husband Name | P.R.Chowdhury
|  |  |  | 19 | Mother Name | A.R.Chowdhury
|  |  |  | 20 | Go to Verification Tab
|  |  |  | 21 | Enter Pan | 111111
|  |  |  | 22 | Enter Voter | 222222
|  |  |  | 23 | Enter Dl | 333333
|  |  |  | 24 | Enter Aadhaar | 444444
|  |  |  | 25 | Enter Passport | 555555
|  |  |  | 26 | Select Form 60 Status | No
|  |  |  | 27 | Select Form 61 | No
|  |  |  | 28 | Go to Address Tab
|  |  |  | 29 | Enter Address | LTI
|  |  |  | 30 | Enter Village Name | Multi Select
|  |  |  | 31 | Enter State | Maharashtra
|  |  |  | 32 | Enter Pincode | 400705
|  |  |  | 33 | Enter Landline Number | 12345678901
|  |  |  | 34 | Enter Mobile Number | 1234567890
|  |  |  | 35 | Enter Mail id | abc@gmail.com
|  |  |  | 36 | Go to Other Tab
|  |  |  | 37 | Enter income | 10000000
|  |  |  | 38 | Enter Education | Multi Select
|  |  |  | 39 | Enter Marital Status | Unmarried
|  |  |  | 40 | Enter Nature Of Activity | Multi Select
|  |  |  | 41 | Click Submit |  | Member Details Saved Sucessfully. Please Upload Photograph.
|  |  |  | 42 | Select Member Id from Member Id List | 118573
|  |  |  | 43 | Choose Image file to upload from System | <Path of image> or <fully qualified name of the image>
|  |  |  | 44 | Click Upload |  | Image Uploaded successfully
|  |  |  | 45 | Select Member Id from Member Id List | 118573
|  |  |  | 46 | Choose Signature Image file to upload from System | <Path of image> or <fully qualified name of the image>
|  |  |  | 47 | Click Upload |  | Image Uploaded successfully
|  |  |  | 48 | Go to membership tab
|  |  |  | 49 | Go to Membership Modification
|  |  |  | 50 | Click on Individual
|  |  |  | 51 | Select Member Id from Member Id List that is yet not confirmed
|  |  |  | 52 | Click actions and then click on confirm
|  |  |  | 53 | Change Value of Land Area as required | 10000
|  |  |  | 54 | Click on Submit |  | Account Successfully Confirmed
9 | TS_FixedDeposit_001 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to Create Fixed Deposit | 1 | Go to Fixed Deposit in Term Deposit
|  |  |  | 2 | Click on Create Fixed Deposit
|  |  |  | 3 | Select Member ID
|  |  |  | 4 | Select Source Account
|  |  |  | 5 | Click on "View Balance" |  | Can view Balance in the Account
|  |  |  | 6 | Select Customer(Type) | 1.Normal/Minor 2.Senior Citizen
|  |  |  | 7 | Select FD Type | Joint | Joint Holder Fields Appears
|  |  |  | 8 | Enter Joint Holder Name | Dishant
|  |  |  | 9 | Select Relation with Joint Holder | 1.Mother 2.Father 3.Brother 4.Sister 5.Spouse 6.Son 7.Daughter 8.Others
|  |  |  | 10 | Enter Nominee Name | Disha
|  |  |  | 11 | Select Relation With Nominee | 1.Mother 2.Father 3.Brother 4.Sister 5.Spouse 6.Son 7.Daughter 8.Others
|  |  |  | 12 | Select Visibility of Relation with Nominee | 1.Hidden 2.Disclose
|  |  |  | 13 | Enter Deposit Time | 963852
|  |  |  | 14 | Enter Tenure (Days)- Y,M,D | 1,6,12
|  |  |  | 15 | Select From Interest Slab | Multiselect
|  |  |  | 16 | Enter Interest Rate | 5%
|  |  |  | 17 | Select Interest Pay Plan | Multiselect
|  |  |  | 18 | Click on "Calculate Maturity Amount" |  | Maturity Amount is generated according to Selected Interest Pay Plan
|  |  |  | 19 | Select "Select Instruction Field" in "At Maturity Area" | Multiselect
|  |  |  | 20 | Click on "Submit Button" |  | Fixed Deposit Created
|  |  |  | 21 | Select FD Type
|  |  |  | 22 | Enter Nominee Name | Disha
|  |  |  | 22 | Select Relation With Nominee | 1.Mother 2.Father 3.Brother 4.Sister 5.Spouse 6.Son 7.Daughter 8.Others
|  |  |  | 23 | Select Visibility of Relation with Nominee | 1.Hidden 2.Disclose
|  |  |  | 24 | Enter Deposit Time | 963852
|  |  |  | 25 | Enter Tenure (Days)- Y,M,D | 1,6,12
|  |  |  | 26 | Select From Interest Slab | Multiselect
|  |  |  | 27 | Enter Interest Rate | 5%
|  |  |  | 28 | Select Interest Pay Plan | Multiselect
|  |  |  | 29 | Click on "Calculate Maturity Amount" |  | Maturity Amount is generated according to Selected Interest Pay Plan
|  |  |  | 30 | Select "Select Instruction Field" in "At Maturity Area" | Multiselect
|  |  |  | 31 | Click on "Submit Button" |  | Fixed Deposit Created
9 | TS_FixedDeposit_002 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to View Fixed Deposit | 1 | Go to Fixed Deposit in Term Deposit
|  |  |  | 2 | Click on "View Fixed Deposit" |  | "View Fixed Deposit" Page Appears
|  |  |  | 3 | Select Member ID | 118981-a c
|  |  |  | 4 | Click on "Submit Button"
10 | TS_FixedDeposit_003 | 1. Internet is accessible 2.site is up 3. there should be an existing account of the user | Able to View Fixed Deposit | 1 | Go to Fixed Deposit in Term Deposit
|  |  |  | 2 | Click on "Close Fixed Deposit" |  | "Close Fixed Deposit" Page Appears
|  |  |  | 3 | Select Action | Multiselect
|  |  |  | 4 | Enter Member ID | 118981-a c
|  |  |  | 5 | Enter Account No. | 9658998489
|  |  |  | 6 | Enter Penaltyt Charge(2%) | 1234
|  |  |  | 7 | Click on "Calculate Closure Amount" |  | Fields will be filled Automatically
|  |  |  | 8 | Click on "Submit Button" |  | Fixed Deposit is Closed
| 1 | TS_Transaction_Receipt/Payment_001 | 1. Internet is accessible. 2.site is up and running. 3. there should be an existing account of the user. | Able to add a transaction After successful login. | 1 | Navigate to receipt payment. Under Transaction > Transaction Entry > click on receipt payment. | -
[5 empty] | 2 | member ID | Select already present ID's from dropdown box.
[5 empty] | 3 | Account Number | Select auto generated account number from dropdown box.
[5 empty] | 4 | Transaction Type | Credit
Debit
[5 empty] | 5 | Transaction Code | SB
CA
[5 empty] | 6 | Amount | Numeric Characters
All Characters except numeric(i.e. character, special characters).
[5 empty] | 7a. | Instrument Type | Cheque | Cheque Number TextBox field appears.
[5 empty] | 7b. |  | Withdrawl Slip | -
[5 empty] | 7c. |  | Charges | Multi Select from dropdown.
[5 empty] | 7d. |  | Receipt | -
Note on D2: Mention pre - conditions as per Test Scenario or Screen element conditions. E.g. 'User is on the Personal Details Page', 'Focus is on First name field'.
Note on E2: Enter the Test Case description.
Note on F2: Enter the Test Step No.
Note on G2: Enter Test Step Description
Note on H2: Enter Test Data for the step.
Note on I2: Enter the result expected on performing the current step.

## Sheet1
TestCasedescription | Keyword | Object locator | ObjectType | value | var | result
Login to Website
| GOTOURL |  |  | http://205.147.102.59:8080/SoftPac/login
| CLICK | user_name | id
| SETTEXT | user_name | id | beta34
| CLICK | password | id
| SETTEXT | password | id | beta@123
| CLICK | #user_login > div.submit_container > input | css
| TIMEOUT |  |  | 1
| GOTOURL |  |  | http://205.147.102.59:8080/SoftPac/login
| CLICK | user_name | id
| SETTEXT | user_name | id | beta8
| CLICK | password | id
| SETTEXT | password | id | beta@124
| CLICK | #user_login > div.submit_container > input | css
| TIMEOUT |  |  | 1
| GOTOURL |  |  | http://205.147.102.59:8080/SoftPac/login
| CLICK | user_name | id
| SETTEXT | user_name | id | beta88
| CLICK | password | id
| SETTEXT | password | id | beta@124
| CLICK | #user_login > div.submit_container > input | css
| TIMEOUT |  |  | 1
| GOTOURL |  |  | http://205.147.102.59:8080/SoftPac/login
| CLICK | user_name | id
| SETTEXT | user_name | id | beta8
| CLICK | password | id
| SETTEXT | password | id | beta@123
| CLICK | #user_login > div.submit_container > input | css
| TIMEOUT |  |  | 1
REGISTRATION
| CLICK | /html/body/div[1]/div[1]/nav/ul/li[1]/a | XPATH
| CLICK | body > div.mm-page > div.submenu > nav > ul > li:nth-child(1) > ul > li:nth-child(1) > a | CSS
| CLICK | /html/body/div[1]/div[1]/nav/ul/li[1]/ul/li[1]/ul/li[2]/a | XPATH
| CLICK | //*[@id="member_types_chosen"]/a/div/b | XPATH
| CLICK | //*[@id="member_types_chosen"]/div/ul/li | XPATH
| CLICK | account_type | id
| CLICK | //*[@id="account_type"]/option[1] | XPATH
| CLICK | name | id
| SETTEXT | name | id | NAMAN MAHAJAN
| CLICK | operator | id
| SETTEXT | operator | id | ABCD
| CLICK | operator2 | id
| SETTEXT | operator2 | id | DCBA
| CLICK | custconstitution | id
| CLICK | //*[@id="custconstitution"]/option[2] | XPATH
| CLICK | details | id
| SETTEXT | details | Id | LAND DETAILS
| CLICK | document | id
| SETTEXT | document | id | RENT AGREEMENT
| CLICK | authority | id
| SETTEXT | authority | id | NOC officer
| CLICK | issue | id
| SETTEXT | issue | id | MAHAPE
| CLICK | register | id
| SETTEXT | register | id | a123456789
| CLICK | datepicker | id
| SETTEXT | datepicker | id | 2018-06-22
| TIMEOUT |  |  | 4
| CLICK | //*[@id="tab_menu_2"]/div | XPATH
| CLICK | pan | id
| SETTEXT | pan | id | EGPM1234
| CLICK | Address1 | id
| SETTEXT | Address1 | id | 36,M.G. ROAD
| CLICK | Address2 | id
| SETTEXT | Address2 | id | DEWAS
| CLICK | //*[@id="custcity_chosen"]/a/div/b | XPATH
| CLICK | //*[@id="custcity_chosen"]/div/ul/li[1] | XPATH
| CLICK | state | id
| SETTEXT | state | id | MAHARASHTRA
| CLICK | pin | id
| SETTEXT | pin | id | 477005
| CLICK | landline | id
| SETTEXT | landline | id | 22212345678
| CLICK | mobile | id
| SETTEXT | mobile | id | 9876543210
| CLICK | email | id
| SETTEXT | email | id | ABCD@GMAIL.COM
| TIMEOUT |  |  | 5
| CLICK | //*[@id="tab_menu_3"]/div | XPATH
| CLICK | income | id
| SETTEXT | income | id | 30
| CLICK | custeducation | id
| CLICK | //*[@id="custeducation"]/option[2] | XPATH
| CLICK | custactmanu | id
| CLICK | //*[@id="custactmanu"]/option[3] | XPATH
| CLICK | submit | id
| TIMEOUT |  |  | 2
| CLICK | //*[@id="M_id_chosen"]/a/div/b | XPATH
| CLICK | //*[@id="M_id_chosen"]/div/ul/li[5] | XPATH
| UPLOAD | file_upload | id
| CLICK | //*[@id="nominee_linkage"]/div[3]/input | XPATH
| CLICK | /html/body/div[1]/div[1]/nav/ul/li[1]/a | XPATH
| CLICK | /html/body/div[1]/div[1]/nav/ul/li[1]/ul/li[2]/a | XPATH
| CLICK | /html/body/div[1]/div[1]/nav/ul/li[1]/ul/li[2]/ul/li[2]/a | XPATH
| HOVER | body > div.mm-page > div.submenu > nav > ul > li:nth-child(2) > a | css
| TIMEOUT |  |  | 1
| HOVER | body > div.mm-page > div.submenu > nav > ul > li:nth-child(2) > ul > li:nth-child(2) > a | css
| CLICK | body > div.mm-page > div.submenu > nav > ul > li:nth-child(2) > ul > li:nth-child(2) > ul > li:nth-child(1) > a | css
| TIMEOUT |  |  | 1
TRANSACTION
| TIMEOUT |  |  | 1
| CLICK | #member_chosen | css
| CLICK | #member_chosen > div > div > input[type="text"] | css
| SELECT | active-result | CLASSNAME
| CLICK | //*[@id="member_chosen"]/div/ul/li[2] | XPATH
| TIMEOUT |  |  | 2
| CLICK | //*[@id="account_chosen"]/a/span | XPATH
| CLICK | #account_chosen > div:nth-child(2) > ul:nth-child(2) > li:nth-child(1) | CSS
| CLICK | //*[@id="transaction_chosen"]/a | XPATH
| CLICK | /html/body/div[1]/div[2]/section/article/form/div/div/div[1]/div/div[6]/div[1]/div/div/ul/li[2] | XPATH
| CLICK | /html/body/div[1]/div[2]/section/article/form/div/div/div[1]/div/div[11]/div[1]/div/a/span | XPATH
| CLICK | /html/body/div[1]/div[2]/section/article/form/div/div/div[1]/div/div[11]/div[1]/div/div/ul/li[1] | XPATH
| CLICK | /html/body/div[1]/div[2]/section/article/form/div/div/div[1]/div/div[6]/div[2]/div/a | XPATH
| SETTEXT | //*[@id="amount"] | XPATH | 123
| TIMEOUT |  |  | 2

## Sheet2
abs